Team 10 — DineCheck (Campus Dining System): One-Page Budget

Revised October 5, 2026. Loaded rate: $60/hour, the instructor-provided rate for CS 4390/5388.

1. Write the assumptions

| Cost Driver / Assumption | Owner |
| --- | --- |
| Campus dining/menu data is available and does not require a complex outside integration. | Developer |
| Web and mobile use one responsive application instead of separate native apps. | Developer |
| Crowd levels and estimated wait times remain outside this project slice. | Project manager |
| Testing and deployment can be completed using the team’s existing development environment. | Developer |
| Project scope stays limited to dining locations, hours, menus, dietary filtering, and item availability. | Project manager |

2. Convert and staff

Planning estimate: 694 team hours (Session 9, PERT) ÷ 130 = 5.34 FTE-months.

| Role | Month 1 | Month 2 | Total |
| --- | --- | --- | --- |
| Project Manager | 0.17 | 0.03 | 0.20 |
| Developers | 2.68 | 1.22 | 3.90 |
| Testing | 0.25 | 0.42 | 0.67 |
| UX / Mobile | 0.41 | 0.16 | 0.57 |
| Total | 3.51 | 1.83 | 5.34 |

3. Price it

| Role | FTE-months | Loaded Rate | Cost |
| --- | --- | --- | --- |
| Project Manager | 0.20 (26 h) | $60/hour | $1,560 |
| Developers | 3.90 (507 h) | $60/hour | $30,420 |
| UX / Mobile | 0.57 (74 h) | $60/hour | $4,440 |
| Testing | 0.67 (87 h) | $60/hour | $5,220 |
| Labor Total | 5.34 (694 h) |  | $41,640 |

Non-labor: hosting $150/month × 2 = $300; tools $300; domain/deployment $100; database/cloud $300; total $1,000. Base build estimate = $41,640 + $1,000 = $42,640.

Operating cost per year: hosting $150 × 12 = $1,800 + maintenance 4 h/month × 12 × $60 = $2,880 = $4,680.

4. Price the risks

| Risk | Chance | Extra hours | EMV |
| --- | --- | --- | --- |
| Menu data needs extra cleanup or access work | 30% | 24 | $432 |
| Stale availability data needs more testing and rework | 25% | 20 | $300 |
| Requests grow the agreed slice | 20% | 30 | $360 |

EMV = chance × extra hours × $60. Contingency reserve = $1,092. Cost baseline = $42,640 + $1,092 = $43,732. Management reserve (5%) = $2,187. Total budget request = $45,919.