Team 10 — DineCheck (Campus Dining System)

One-Page Budget and ROI Analysis

Revised October 5, 2026. Loaded rate: $60/hour, the instructor-provided rate for CS 4390/5388.

1. Write the assumptions

| Cost Driver / Assumption | Owner |
| --- | --- |
| Campus dining/menu data is available and does not require a complex outside integration. | Developer |
| Web and mobile use one responsive application instead of separate native apps. | Developer |
| Crowd levels and estimated wait times remain outside this project slice. | Project manager |
| Testing and deployment can be completed using the team’s existing development environment. | Developer |
| Project scope stays limited to dining locations, hours, menus, dietary filtering, and item availability. | Project manager |

2. Convert and staff

From Session 9, our planning estimate is 694 team hours. This is the expected (PERT) value from our revised estimation worksheet, which gives a range of 294 to 1,150 hours.

694 ÷ 130 = 5.34 FTE-months (130 productive hours per FTE-month)

| Role | Month 1 | Month 2 | Total |
| --- | --- | --- | --- |
| Project Manager | 0.17 | 0.03 | 0.20 |
| Developers | 2.68 | 1.22 | 3.90 |
| Testing | 0.25 | 0.42 | 0.67 |
| UX / Mobile | 0.41 | 0.16 | 0.57 |
| Total | 3.51 | 1.83 | 5.34 |

3. Price it

694 hours × $60/hour = $41,640 (5.34 FTE-months at $7,800 per FTE-month, which is $60 × 130 hours)

| Role | FTE-months | Loaded Rate | Cost |
| --- | --- | --- | --- |
| Project Manager | 0.20 (26 h) | $60/hour | $1,560 |
| Developers | 3.90 (507 h) | $60/hour | $30,420 |
| UX / Mobile | 0.57 (74 h) | $60/hour | $4,440 |
| Testing | 0.67 (87 h) | $60/hour | $5,220 |
| Labor Total | 5.34 (694 h) |  | $41,640 |

Non-Labor Costs

| Item | How computed | Cost |
| --- | --- | --- |
| Hosting / infrastructure | $150/month × 2 months | $300 |
| Developer / Testing tools | Project allowance | $300 |
| Domain/deployment setup | Project allowance | $100 |
| Database/cloud services | Project allowance | $300 |
| Non-Labor Total |  | $1,000 |

Base Build Estimate = Labor + Non-Labor = $41,640 + $1,000 = $42,640

4. Price the risks

| Risk | Chance | Extra hours | EMV |
| --- | --- | --- | --- |
| Menu data needs extra cleanup or access work | 30% | 24 | $432 |
| Stale availability data needs more testing and rework | 25% | 20 | $300 |
| Requests grow the agreed slice | 20% | 30 | $360 |
| Contingency reserve |  |  | $1,092 |

EMV = chance × extra hours × $60. Chances and extra hours are team assumptions carried from our September 29 draft budget. The project manager controls contingency; the sponsor controls management reserve.

| Line | How computed | Amount |
| --- | --- | --- |
| Base build estimate | Labor + non-labor | $42,640 |
| Contingency reserve | Sum of EMV | $1,092 |
| Cost baseline | Base + contingency | $43,732 |
| Management reserve | 5% of the cost baseline | $2,187 |
| Total budget request | Baseline + management reserve | $45,919 |

Sanity check: one PERT spread from the estimate is about 143 hours ($8,560). Contingency covers the three named risks, not a normal estimating miss.

5. Operating cost (per year, separate from the build)

| Item | How computed | Cost |
| --- | --- | --- |
| Hosting / infrastructure | $150/month × 12 months | $1,800 |
| Maintenance | 4 hours/month × 12 × $60 | $2,880 |
| Operating Total |  | $4,680 |

Staff time spent marking items sold out is not included. It is an adoption risk covered in the business case.

6. ROI analysis

DineCheck does not sell anything, so the return is the value of wasted trips students no longer make. Every input below is an assumption except the wage.

| Input | Value | Basis |
| --- | --- | --- |
| Students who check DineCheck in a week | 500 | Assumption |
| Wasted trips avoided per user per week | 0.5 | Assumption (one every two weeks) |
| Minutes saved per avoided trip | 15 | Assumption, below the 25-minute walk in our interviews |
| Value of an hour of student time | $7.25 | U.S. federal minimum wage |
| Teaching weeks per year | 30 | Assumption (two 15-week semesters) |
| Benefit horizon | 3 years | Assumption, as in Session 11 |

Return: 500 × 0.5 × 30 = 7,500 avoided trips a year. 7,500 × 15 minutes ÷ 60 = 1,875 hours × $7.25 = $13,594 a year, or $40,781 over three years.

| Line | How computed | Amount |
| --- | --- | --- |
| Total cost, 3 years | $45,919 + 3 × $4,680 | $59,959 |
| Total return, 3 years | 3 × $13,594 | $40,781 |
| Net | Return − cost | −$19,177 |
| ROI | Net ÷ cost | −32% |

Break-even: about 735 weekly users, or about 22 minutes saved per avoided trip, with the other inputs unchanged.

7. Sensitivity

Every 100 weekly users is worth about $8,156 over three years. Build size matters as well: at the low end of the estimate (294 hours) the three-year ROI is +17%; at the high end (1,150 hours) it is −54%.

| Weekly users | 10 min saved | 15 min saved | 25 min saved |
| --- | --- | --- | --- |
| 250 | −77% | −66% | −43% |
| 500 | −55% | −32% | +13% |
| 1,000 | −9% | +36% | +127% |

Left out on purpose: money students spend when a plan falls through and any benefit to dining services. We have no basis for averaging them yet. Sources: Session 11 Part 1, Building the Budget, slides 27 to 39; U.S. Department of Labor federal minimum wage.